## Testing
Date | Test ID | Purpose | Steps | Input | Expected Output | Actual Output
2019-07-15 | 1 | Testing Decimal Addition | Click one number then addition then another number | 1+1 | 2 | 2
2019-07-15 | 2 | Testing Decimal Multiplication | Click one number then multiplication then another number | 3*4 | 12 | 12
2019-07-15 | 3 | Testing Decimal subtaction | Click one number then subtration then another number | 15-20 | -5 | -5
2019-07-15 | 4 | Testing Decimal division | Click one number then division then another number | 3/4 | 0.25 | 0
2019-07-16 | 5 | Changing between number systems | Click through the different options of nunmber systems | click on option dots | same value on different number systens appear on output | value on output changes according to number system
2019-07-16 | 6 | limitations on inputs depending on number system choice | Click through the different options of nunmber systems | click on radio buttons | different inputs get greyed out depending on number system | restricted inputs are greyed out
2019-07-17 | 7 | C button clears output and previous operations | Perform an operation | 1+1, C | 0 | 0
2019-07-19 | 8 | test CE button clears current input | click inputs press CE | 256,CE | 0 | 0
2019-07-19 | 9 | test power button | input number press ^ | 4,^2 | 16 | 16
2019-07-19 | 10 | test square root button | input number press ?x | 16,?x | 4 | 4
2019-07-19 | 11 | test square button | input number then press x² | 3,x² | 9 | 9
2019-07-19 | 12 | test copy and paste buttons | input numbers copy clear screen paste | 65,copy,C,paste | 65 | 65
2019-07-19 | 13 | 1st and 2nd compliments | input binary number | switch to binary, 1001 | 111 | 111
2019-07-19 | 14 | Testing the functionality of the new UI | perform all the previous tests with the new ui | click through all the operations and perform actions | no errors and correct outputs | Some buttons don’t have proper functionality
2019-07-19 | 15 | Retesting UI functionality | perform all the previous tests with the new ui | click through all the operations and perform actions | no errors and correct outputs | no errors and correct outputs
2019-07-19 | 16 | Testing main menu click through to calculator | open program, click on calculator button | click calculator button | calculator window to open and work | calculator opens without error and works as expected
2019-07-20 | 17 | Test new snake game modes | open program and test different snake versions | click snake then click bin,hex,oct | proper treats appearing for the num systems | correct numbers do not appear
2019-07-20 | 18 | Test new snake game modes | open program and test different snake versions | click snake then click hex,oct | proper treats appearing for the num systems | bin works, hex does not
2019-07-20 | 19 | Test new snake game modes | open program and test different snake versions | click snake then click bin,hex,oct | proper treats appearing for the num systems | proper treats appear
2019-07-23 | 20 | test new 2048 game | open program and click new button | click newly added button | game functions like the app game | tiles ad up and more correctly
2019-07-23 | 21 | Test new 2048 game modes | open program and test different 2048 versions | click 2048 then click different version | proper tile values appear and interact | Only octal is being used
2019-07-23 | 22 | Test new 2048 game modes | open program and test different 2048 versions | click 2048 then click different version | proper tile values appear and interact | Only octal is being used
2019-07-23 | 23 | Test new 2048 game modes | open program and test different 2048 versions | click 2048 then click different version | proper tile values appear and interact | Only bin is being used
2019-07-23 | 24 | Test new 2048 game modes | open program and test different 2048 versions | click 2048 then click different version | proper tile values appear and interact | all work but have improper fonts
2019-07-23 | 25 | Test new 2048 game modes | open program and test different 2048 versions | click 2048 then click different version | proper tile values appear and interact | all versions work properly
2019-07-24 | 26 | Test new added quiz game | open click new quiz button | click quiz and test game | answers randomize and are the correct answers | answer was always on C, UI was improper
2019-07-24 | 27 | Test quiz ui | open quiz game | click quiz and test game | ui fits and looks like other windows | ui looks proper and themed
2019-07-26 | 28 | test dark mode theme | open calculator click new menu click dark mode | click calculator button, click dark mode theme menu button | colors change to dark mode | ui chnages to dark mode version
2019-07-29 | 29 | test new quiz modes | open quiz game click different mode | click quiz then click bin,hex,oct | questions corresponds with correct number system | application crashes
2019-07-31 | 30 | test new quiz modes | open quiz game click different mode | click quiz then click bin,hex,oct | questions corresponds with correct number system | different modes work correctly
2019-08-01 | 31 | test new snake UI | open snake | click snake then click bin,hex,oct | proper treats appearing for the num systems | correct numbers do not appear